## Sheet1
Bug Log Report
Ttrack
Bug Number | Severity Level | Date Created | Section | Description | Identified by | How to replicate | Status | Resolution | Fixed On | Fixed By
B-001 | High | 2025-08-05 | Upload | Crash on upload with empty file | Luis | Create an empty xlsx and try to use as transcript. | Open | Fixed | 2025-07-31 | Luis
B-002 | Medium | 2025-08-05 | Curriculum | Missing elective name causes exception | Victor | Having the field empty is generating a crash | Open | Investigating | TBD | Luis
B-003 | High | 2025-08-06 | Theme | Dark mode flickers | Nomayer | Open on windows and switch between light and dark mode | Closed | Fixed | 2025-08-05 | Luis
B-004 | Low | 2025-08-06 | Matching | Mismatch count doesn't update | Rosa | Ran the match with 2 subjects mismatched and it showed only 1 | Closed | Fixed | 2025-08-06 | Luis
B-005 | Medium | 2025-08-07 | Export | Filename not suggested in export | Hussain | Download option had users to write in the name of the file. Can we make it automatic? | Resolved | Improved | 2025-08-06 | Luis